## Test Reports
TEST PLAN & PROGRESS REPORT
ID | Test Name | Responsibility | Dead Line | Status | Comments | Date completed
1 | Guess The Word - Play Game | Ivan Staev | March 1st | completed |  | Feb 28th
2 | Guess The Word - How to play (Menu) | Teodora Kompanska | March 1st | completed |  | Feb 27th
3 | Guess The Word - In Game (Menu) | Teodora Kompanska | March 1st | completed |  | Feb 28th
4 | Hangman - Play Game | Ivan Staev | March 1st | completed |  | Feb 11th
5 | Hangman - How to play (Menu) | Marieta Stoycheva | March 1st | completed |  | Feb 22nd
6 | Hangman - In Game (Menu) | Teodora Kompanska | March 1st | completed |  | Feb 20th
7 | Main Menu - Switching to Hangman | Marieta Stoycheva | March 1st | completed |  | Feb 12th
8 | Main Menu - Switching to Guess the Word | Marieta Stoycheva | March 1st | completed |  | Feb 12th
9 | Main Menu - Quit | Marieta Stoycheva | March 1st | failed | Error when you try to close the application: "Invalid move. Please try again:" | Feb 12th
10 | Main Menu - Quit | Marieta Stoycheva | March 1st | completed |  | Feb 28th